MERZA BRAND

Complete CRM & Business Automation

PROJECT PLAN

Premium Tropical Fruits  |  E-Commerce  |  AI-Powered CRM  |  Marketing Automation

Prepared by Viviz Technologies

viviztechnologies@gmail.com

June 2026

# 1. Brand Overview

| Brand | Merza |
| --- | --- |
| Niche | Premium Tropical Fruits (B2C + B2B) |
| Products | Premium Mangoes, Banana Red, Vietnam Gold Jackfruit, Freeze Dried, Pulp |
| Current Channel | Meta Paid Ads (Facebook + Instagram) |
| Goal | Full-stack business automation — ads bot, ecommerce, CRM, marketing engine |
| Timeline | 20 Weeks (5 Months) |
| Prepared by | Viviz Technologies ¦ June 2026 |

## Product Catalog

| Product | Variants | Type |
| --- | --- | --- |
| Premium Mangoes | 1 kg, 2 kg, 5 kg box | Perishable |
| Banana Red | 1 kg, 3 kg | Perishable |
| Vietnam Gold Jackfruit | Whole, Seeded packs | Perishable |
| Freeze Dried (Mango, Jackfruit) | 100 g, 250 g pouch | Non-perishable |
| Pulp (Mango, Jackfruit) | 500 g, 1 kg tub | Frozen |

# 2. Tech Stack

| Layer | Technology |
| --- | --- |
| E-commerce Frontend | Next.js 15 + Tailwind CSS + shadcn/ui |
| Admin CRM Panel | Next.js 15 + shadcn/ui Dashboard |
| Backend API | Laravel 11 (PHP 8.3) — REST + Webhooks |
| Bot Engine | Python FastAPI + Claude API (claude-sonnet-4-6) |
| Database | PostgreSQL 17 |
| Cache & Queues | Redis + Laravel Queues |
| Real-time | Pusher / Laravel Echo |
| Meta Integration | Facebook Graph API v21 + Webhooks |
| WhatsApp | Meta Cloud API (WhatsApp Business) |
| Voice Bot | Twilio Voice + Claude AI |
| Email | Mailgun or Resend |
| SMS | Twilio SMS |
| Payments | Stripe + local payment gateway |
| File Storage | Cloudflare R2 / AWS S3 |
| AI Engine | Claude API (claude-sonnet-4-6) |
| Automation | n8n (self-hosted) |

# 3. Core Modules

MODULE 1    —  Meta Ads Campaign Bot

Auto-replies to every Facebook/Instagram ad comment and DM within seconds using Claude AI.

### Key Features

- Facebook/Instagram Webhook listener (comment + DM triggers)

- AI-powered reply generation — context-aware, brand-voice trained

- Smart conversation flows: Greeting → Product inquiry → Pricing → Order link → Payment

- FAQ automation: delivery areas, minimum order, shelf life

- Negative comment de-escalation + move to DM

- Lead capture: name, number, product interest → auto-created in CRM

- Human escalation when sentiment score drops below threshold

- Reply speed control: instant or humanized 30–90 s delay

- Comment moderation: spam and competitor detection

- Reply template library with A/B variants

- Multi-language support (English + local)

MODULE 2    —  WhatsApp Business Bot

Full conversational commerce — catalog, orders, payments, and delivery updates inside WhatsApp.

### Key Features

- Auto-reply to incoming WhatsApp messages with interactive menus

- Product catalog browsing directly inside WhatsApp

- Order placement flow: Browse → Select qty/variant → Address → Payment link → Confirmation

- Broadcast campaigns (bulk messages to segmented contact lists)

- Automated sequences: Welcome, Abandoned cart (1 h / 24 h / 72 h), Delivery updates, Review request, Win-back (30-day inactive)

- Opt-in/opt-out management (GDPR compliant)

- Bot to human handoff with staff assignment

MODULE 3    —  Voice Bot

AI phone agent handling inbound calls from customers sourced via Meta ads.

### Key Features

- Twilio phone number integration with Claude-powered natural language understanding

- Call flows: Order status, New order placement, Complaints — all via natural speech

- Order lookup by phone number or order ID

- Complaint logging auto-created as CRM support ticket

- Call recording + transcript saved to customer record

- Voicemail transcription with auto-response via WhatsApp

- Business hours routing — after-hours to voicemail

- Call analytics: total calls, avg duration, resolution rate

MODULE 4    —  E-commerce Storefront

Public-facing branded Merza website with full product catalog and online ordering.

### Pages

- Home — Hero, featured products, seasonal offers, testimonials, WhatsApp CTA

- Products — Filterable grid by type, price, availability

- Product Detail — High-res images, nutritional info, origin story, reviews, quantity selector

- Cart & Checkout — Multi-step, address autocomplete, delivery date picker, promo codes

- Payment — Stripe card, bank transfer, COD option

- Order Tracking — Real-time status page (Ordered → Packed → Shipped → Delivered)

- Customer Account — Order history, saved addresses, loyalty points, referral link

- Blog / Recipes — SEO content (e.g. 'best mango smoothie recipe')

- B2B Inquiry — Bulk order form for hotels, restaurants, juice bars

- Mobile-first responsive design, PWA-ready

MODULE 5    —  CRM Core

Central hub for all customer data, leads, and sales pipeline management.

### Contacts & Customers

- Unified profile merging all channels (FB DM, WhatsApp, website, phone)

- Purchase history, LTV, average order value

- Tags & segments: VIP, first-time, bulk buyer, dormant

- Full activity timeline — every interaction logged

### Lead Pipeline

- Kanban: New Lead → Contacted → Interested → Quote Sent → Ordered → Loyal

- Auto-move on actions (e.g., order placed = move to Ordered stage)

- Lead scoring based on engagement, response speed, order value

- Assignment to sales staff with follow-up task auto-creation

MODULE 6    —  Product & Inventory Management

Full product catalog, stock tracking, and seasonal availability management.

### Key Features

- Product catalog with variants: 500 g, 1 kg, 2 kg box, 5 kg box

- SKU management + barcode support

- Stock level tracking with low-stock alerts

- Seasonal availability calendar (mango season, harvest dates)

- Cost price + selling price + margin calculator

- Batch/expiry tracking (critical for perishables + freeze dried)

- Supplier management and reorder triggers

MODULE 7    —  Order & Delivery Management

Full order lifecycle from placement to doorstep delivery.

### Order Workflow

- Order creation: auto from website/WhatsApp + manual entry

- Workflow: Pending → Confirmed → Packed → Dispatched → Delivered → Completed

- Auto-generated PDF invoices

- Delivery zone mapping with rider/courier assignment

- Real-time delivery tracking link sent via WhatsApp

- Proof of delivery (photo upload by rider)

- COD cash collection tracking

- Returns & refund workflow with partial fulfillment support

MODULE 8    —  Marketing Automation Engine

Run, schedule, and automate all campaigns across WhatsApp, email, Meta, and SMS.

### Campaign Types

| Campaign | Trigger | Channel |
| --- | --- | --- |
| Welcome Sequence | First purchase | WhatsApp + Email |
| Abandoned Cart | No checkout after 1 h | WhatsApp + SMS |
| Seasonal Flash Sale | Manual or date-based | WhatsApp + Email |
| Cross-sell | Bought Mangoes | WhatsApp |
| Win-back | 30 days no order | WhatsApp + Email |
| VIP Offer | LTV above threshold | WhatsApp personal |
| Review Request | 2 days post-delivery | WhatsApp |
| Referral Program | Any customer | WhatsApp + Email |
| B2B Nurture | Bulk inquiry form | Email sequence |

### Meta Ads Sync

- Export high-LTV customers as Meta Custom Audience

- Auto-build Lookalike Audiences from top customers

- UTM tracking on all links for revenue attribution per ad

- Sync Meta lead form submissions directly to CRM

MODULE 9    —  Analytics & Reporting Dashboard

Business intelligence across all touchpoints — revenue, customers, marketing, and operations.

### Revenue Dashboard

- Total revenue (today / week / month / year)

- Revenue by product and by channel (website, WhatsApp, phone, Meta leads)

- Average order value trend and repeat purchase rate

### Customer Dashboard

- New vs. returning customers

- Customer LTV distribution and churn risk segments

- Top customers by spend and geographic heat map

### Marketing Dashboard

- Ad spend vs. revenue (ROAS) and cost per lead by campaign

- Bot conversation completion rate

- WhatsApp broadcast open/click rates and email stats

### Operations Dashboard

- Orders by status and average fulfillment time

- Delivery success rate and low-stock alerts

- Staff performance: leads handled, orders processed

# 4. Marketing Brainstorm — Growing Merza via CRM

## 10 Key Marketing Strategies

| # | Strategy | Description |
| --- | --- | --- |
| 1 | Seasonal Spikes | Tag mango season peaks (April–June) in the product calendar. Auto-trigger WhatsApp blasts 2 weeks before peak. Schedule Meta ad creative rotation synced to harvest dates. |
| 2 | B2B Revenue Stream | Separate CRM pipeline for restaurants, hotels, juice bars. Bulk pricing tiers auto-calculated in quotes. Monthly standing order automation. |
| 3 | Subscription Box | Monthly curated premium fruit box at discounted price with auto-billing. Churn prevention via pause option. |
| 4 | UGC Social Proof Loop | Post-delivery WhatsApp: 'Send us a photo for 15% off next order!' UGC stored in CRM, best content exported for Meta ad creative. |
| 5 | Referral Engine | Every customer gets a unique referral link tracked in CRM. Top referrers flagged as Brand Ambassadors. |
| 6 | Freeze Dried as E-gift | Corporate gifting campaigns (gift box builder on site). Target October–December festival season. |
| 7 | WhatsApp Segments | Mango lovers, Premium tier, Lapsed (21-day), New prospects — each with tailored broadcast cadence. |
| 8 | Meta Retargeting Funnel | Cold → Ad → Bot → Lead → WhatsApp sequence → First order → Loyalty → Referral + Lookalike → Cold. |
| 9 | Recipe Content Marketing | Blog posts ranking on Google (e.g. '5 smoothie recipes with Merza Mango Pulp'). Organic traffic → CRM lead capture. |
| 10 | Festival Campaigns | Eid, Diwali, Christmas gift box campaigns. Pre-built templates with auto-SMS/WhatsApp blast 1 week before festival. |

# 5. Project Phases & Timeline

| Phase | Name | Timeline | Deliverables |
| --- | --- | --- | --- |
| Phase 1 | Foundation | Weeks 1–3 | Repo setup, DB schema, Laravel 11 API boilerplate + JWT auth, Redis, admin panel shell, role-based access (Admin, Sales, Operations, Delivery) |
| Phase 2 | Product & Inventory | Weeks 3–5 | Product CRUD with variants and pricing, inventory tracking with low-stock alerts, seasonal availability calendar, CSV import/export |
| Phase 3 | E-commerce Storefront | Weeks 4–8 | Next.js public storefront, product listing + detail pages, cart & checkout, Stripe integration, order tracking page, customer account portal, mobile optimization |
| Phase 4 | CRM Core | Weeks 6–9 | Contact management with unified profiles, Kanban lead pipeline, activity timeline, lead scoring engine, deal/quote management |
| Phase 5 | Order & Delivery | Weeks 8–10 | Order workflow engine, PDF invoice generation, delivery assignment, real-time tracking, COD tracking, returns management |
| Phase 6 | Meta Ads Bot | Weeks 9–12 | Facebook Graph API webhooks, comment auto-reply engine via Claude, DM conversation flow builder, lead auto-capture to CRM, human escalation |
| Phase 7 | WhatsApp Bot | Weeks 11–14 | Meta Cloud API setup, interactive menu builder, order-via-WhatsApp flow, broadcast campaigns, automated sequences (cart, win-back, review) |
| Phase 8 | Marketing Automation | Weeks 13–16 | Drag-and-drop campaign builder, audience segmentation, email campaigns (Mailgun), Meta Custom Audience sync, UTM tracking, A/B testing |
| Phase 9 | Voice Bot | Weeks 15–17 | Twilio Voice integration, Claude-powered call handler, order status IVR, call recording + CRM logging, after-hours voicemail |
| Phase 10 | Analytics | Weeks 16–18 | Revenue dashboard, customer analytics, marketing ROI dashboard, operations metrics, automated weekly email reports |
| Phase 11 | QA & Launch | Weeks 18–20 | End-to-end testing of all flows, performance optimization, staff training, production go-live, monitoring setup |

Total Timeline:  20 Weeks  (5 Months)

# 6. Project Structure

D:\projects\merza-crm\ ├── apps/ │ ├── storefront/ # Next.js 15 — public e-commerce site │ ├── admin/ # Next.js 15 — CRM admin panel │ └── bot-engine/ # Python FastAPI — Claude AI bot ├── api/ # Laravel 11 — core REST API │ ├── app/ │ │ ├── Models/ # Customer, Order, Product, Lead, Campaign... │ │ ├── Http/Controllers/ │ │ ├── Jobs/ # Queue workers (WhatsApp, email, Meta sync) │ │ └── Services/ # MetaBot, WhatsAppBot, VoiceBot, Analytics │ ├── database/migrations/ │ └── routes/api.php ├── infrastructure/ │ ├── docker-compose.yml │ └── nginx/ └── docs/ ├── api-spec.md └── bot-flows.md

# 7. External API Accounts Required

| Service | Purpose | Cost Model |
| --- | --- | --- |
| Meta for Developers | Facebook/Instagram Webhooks, WhatsApp Business API | Free (usage-based) |
| Twilio | Voice bot, SMS campaigns | Pay-per-use |
| Stripe | Online payments and subscriptions | 2.9% + $0.30/txn |
| Mailgun / Resend | Transactional and campaign emails | Free tier then paid |
| Cloudflare R2 | Product image and media storage | $0.015/GB |
| Claude API | AI bot intelligence across all channels | Usage-based |
| n8n (self-hosted) | Workflow and marketing automation engine | Free (self-hosted) |

## Recommended Starting Point

Phase 1 — Foundation:  Create the monorepo at D:\projects\merza-crm, design the full database schema, scaffold the Laravel 11 API with JWT auth, set up Redis queues, and build the admin panel shell with role-based access control.

— Prepared by Viviz Technologies —

viviztechnologies@gmail.com  |  June 2026